## Gantt Chart
Project 5 — TCR Violations Analysis: Gantt Chart
# | Task | Description | Week 1 | Week 2 | Week 3 | Week 4 | Week 5
1 | 1. Data Acquisition | Download SDWIS CSV files for 5 states | Done
2 | 2. Data Cleaning | Import, clean, and standardize data in Python | Done
3 | 3. Size Classification | Define classify_size() function, apply to dataset |  | Done
4 | 4. Summary Statistics | Compute violations by state and system size |  | Done
5 | 5. Figure 1 — Bar Charts | Total & avg violations per state |  |  | Done
6 | 6. Figure 2 — Small vs Large | Grouped bar chart comparing system sizes |  |  | Done
7 | 7. Figure 3 — Map | Choropleth map using geopandas |  |  | Done
8 | 8. Discussion & Bias | Write analysis, literature review, coding bias section |  |  |  | In Progress
9 | 9. Scope of Work | Draft and finalize SOW document |  |  |  | Done
10 | 10. Gantt Chart | Create project timeline |  |  |  | Done
11 | 11. Timesheet | Log hours for all tasks |  |  |  |  | In Progress
12 | 12. Executive Summaries | Write technical and non-technical summaries |  |  |  |  | In Progress
13 | 13. Final Review | Review all deliverables before submission |  |  |  | Not Started | Done
Legend: | > Done | > In Progress | > Not Started